## Introduction
Scrum Excel Helper Workbook
What is this? | This workbook is meant to help you manage your scrum project, as a scrum master. It can help you keep track of the product backlog, sprint backlogs, and displays the burndown chart for each sprint. (If you don't know what all those mean, read the next point.) I've kept it very basic so that you can easily extend it to suit your needs. If you have any suggestion for improvement or other coment I'd like to hear from you.
Where can I learn more about Scrum? | Scrum in 5 minutes (PDF) from softhouse
Scrum Cheat Sheet (PDF) from agile42
How do I use it? | Before project start: the product owner is responsible for managing the product backlog. Enter all user stories, with the associated priority, in the "Product backlog" sheet. Don't fill the "Sprint" column yet
Before each sprint: after you have conducted a sprint planing meeting, fill the "Sprint #" column of the product backlog to reflect which user stories will be addressed in this sprint. Copy the previous Spring sheet into a new sheet. Break down the user stories into tasks and assign them a priority and an estimate in scrum units.
After each work day: fill in the actual remaining scrum units for each of this sprint's task. Check the burndown chart.
Notes | Cells than you can edit use a blue background.
Sprints are assumed to be 2 weeks long (10 working days), excluding weekends; if it is not the case you'll have to adjust the Sprint sheets accordingly.
Some cells (like this one) have comments (little red triangle at the top right corner). Read them!
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. It incorporates the following main changes:
- no need to have a separate system sheet, Spring sheets are self-contained
- remaining units computation was fixed (should reflect the situation at the end of the day)
See original post on "Le Touilleur Express"
Author | Olivier Gérardin
Technical director and Java architect
E-mail me: olivier@gerardin.info
My blog: blog.gerardin.info
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Note on B17: Olivier Gérardin: Read the cell comments!

## Product backlog
Product Backlog
| Organization | Flinders University MDT2018
| Project | Mitch the Lich
| Scrum Master | Olivier Gérardin
| Product Owner | Marcel Marceau
Story ID | Title | User story | Priority | Sprint # | Completed
1 | Game world | As a dev I want to have a game world so I can push and pull to a repository. CoS: commit and pull from Github | 10 | 1 | 1
2 | UI_Health | As a player I want to see a health bar | 3 | 1 | 1
3 | UI_Map | As a player I want to see a map (do we need a map?) | 1 | 1 | 0
4 | char_control | As a player I want to control my character. | 10 | 2 | 0
5 | char_model | As a player I want to see my character model | 5 | 2 | 0
6 | ui_menu | As a player I want to navigate menus so that I can choose what to do | 5 | 2 | 0
7 | world_arena | As a dev I want to have a level bult so I can test stuff | 10 | 2 | 0
8 | world_camera | As a player I want the camera to stay at a pleasant angle | 7 | 1 | 1
9 | Level01_arena | As a player I want to be in a Shire themed Arena | 5 | 2
10 | Level01_Linear | As a player I want to Play through Level 1 | 5 | 2
11 | Level01_create | As a dev I want to have level 1 created so I can test | 9 | 2
12 | Movement Smoothing | As a payer I want to have smooth movements | 2 | 2
13 | Global_Lighting_Settings | As a player I want to enjoy the environment | 2
14 | Dialogue_Boxes | As a player I want to see dialogue | 2
|  | As a player I want to switch elements | 5
|  | Hide mouse ursor and use ray as a targeting element | 5
|  | As a dev I want to drain mana from an entity when it attacks | 2
|  | As a player I want to create a hitscan beam | 8
|  | As a dev I want to hide the mouse cursor | 5
As a player I want to see particle effects
As a player I want to paint blood on the terrain
|  | As a dev I want to display shadows and global lighting | 8
|  | As a dev I want bunnies to move and lunge at the player | 9
|  | As a player I want to shoot a fireball | 10
As a dev I want to have animation states set so I can modify them
|  | As a player I want to apply buffs and debufs | 8
|  | As a player I want to blink to move quicker | 6
Note on A10: Olivier Gérardin: A unique ID to refer to this story. Doesn't have to be numeric.
Note on B10: Olivier Gérardin: A short title just enough to recall the story.
Note on C10: Olivier Gérardin: (from product owner) Description of the user story in common language. Keep it short (one or wo sentences). Usually formatted as: "As a <role> I want to <function> so that <benefit>".
Note on D10: Olivier Gérardin: (from product owner) Priority of this story. Use an open scale so you can always move priorities later.
Note on E10: Olivier Gérardin: Fill in after Sprint Planning Meeting

## Totals
Sprint Week |  | 1 |  |  |  | 2 |  |  |  | 3 |  |  |  | 4 |  |  |  | 5 |  |  |  | 6 |  |  |  | 7 |  |  |  | 8 |  |  |  | 9 |  |  |  | 10
Team Member | Velocity % | Sprint Total | Completed | Total Units | Comp. Units | Sprint Total | Completed | Total Units | Comp. Units | Sprint Total | Completed | Total Units | Comp. Units | Sprint Total | Completed | Total Units | Comp. Units | Sprint Total | Completed | Total Units | Comp. Units | Sprint Total | Completed | Total Units | Comp. Units | Sprint Total | Completed | Total Units | Comp. Units | Sprint Total | Completed | Total Units | Comp. Units | Sprint Total | Completed | Total Units | Comp. Units | Sprint Total | Completed | Total Units | Comp. Units
Brandon |  | 4 | 4 | 4 | 4 | 4 | 4 | 19 | 19 | 3 | 3 |  |  | 2 | 3 |  |  | 2 | 2 |  |  | 1 | 1 |  |  | 1 | 1
Tim |  | 0 | 1 |  |  | 0 | 2 |  |  | 0 | 3 |  |  | 1 | 4 |  |  | 3 | 4 |  |  | 0 | 1 |  |  | 0 | 1
Jake |  | 0 | 2 |  |  | 1 | 2 |  |  | 0 | 3 |  |  | 0 | 3 |  |  | 2 | 4 |  |  | 1 | 2 |  |  | 1 | 2
Liam |  | 0 | 2 |  |  | 0 | 1 |  |  | 0 | 2 |  |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 1 |  |  | 0 | 1
Owen |  | 4 | 4 |  |  | 3 | 3 |  |  | 2 | 4 |  |  | 2 | 2 |  |  | 2 | 2 |  |  | 3 | 3 |  |  | 3 | 3
Seth |  | 0 | 2 |  |  | 0 | 2 |  |  | 2 | 4 |  |  | 0 | 2 |  |  | 0 | 2 |  |  | 0 | 3 |  |  | 0 | 3

## Sprint 1
Sprint #1Tracking Sheet
|  | Project | Mitch the Lich
|  | Sprint # | 1
|  | Start date | 27/8/2018
Sprint Week
|  |  |  | 1 | 2 | 3 | 4 | 5
Task ID | Story ID | Description | Initial estimate | Friday | Monday | Tuesday | Wednesday | Thursday | Assigned to | Completed |  | Velocity | Stories | VelocityPercent
1 | 1 | Create a repo and a unity project | 0 | 0 |  |  |  |  | Brandon | 1 | Brandon | 4 | 4 | 100
2 | 1 | Push and pull from the repo | 0 | 0 |  |  |  |  | Brandon | 1 | Tim | 0 | 1 | 0
|  | Camera at 45deg | 2 | 1 | 1 | 0 |  |  | Brandon | 1 | Jake | 0 | 2 | 0
4 | 4 | move character in 1 dimension (W+S) | 2 | 2 | 2 | 0 |  |  | Brandon | 1 | Liam | 0 | 2 | 0
5 | 3 | See health bar UI | 1 | 2 | 2 |  |  |  | Tim | 0 | Owen | 4 | 4 | 100
6 | 5 | Import character model placeholder | 1 | [5 empty] | Jake | 0 | Seth | 0 | 2 | 0
7 | 6 | Import model asset | 3 | [5 empty] | Jake | 0
8 | 4 | Create projectile | 3 | [5 empty] | Liam | 0
|  | Move projectile | 2 | [5 empty] | Liam | 0
|  | Boot into main menu | 2 | 0 |  |  |  |  | Owen | 1
|  | Navigate to another menu and back | 2 | 0 |  |  |  |  | Owen | 1
|  | Create scene | 1 | 1 | 1 | 0 | 0 | 0 | Seth | 0
|  | model arena | 5 | 5 | 4 | 2 | 0 | 0 | Seth | 0
|  | Spawn into level from menu | 2 | 0 |  |  |  |  | Owen | 1
|  | Despawn out of level to menu | 2 | 0 |  |  |  |  | Owen | 1
|  | Remaining units (actual) | 28 | 11 | 10 | 2 | 0 | 0
|  | Remaining units (ideal) |  | 11.2 | 8.4 | 5.6 | 2.8 | 0
[11 empty] | 0 | 14
[11 empty] | 5 | 0
Note on D5: Olivier Gérardin: The sprint number.
Note on D6: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on A10: Olivier Gérardin: A unique Task ID
Note on B10: Olivier Gérardin: The Story this task will help complete.
Note on D10: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E10: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C31: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D31: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C32: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.

## Sprint 2
Sprint #2Tracking Sheet
|  | Project | Mitch the Lich
|  | Sprint # | 2
|  | Start date | 2018-09-03
Sprint Week
|  |  |  | 1 | 2 | 3 | 4 | 5
Task ID | Story ID | Description | Initial estimate | Friday | Monday | Tuesday | Wednesday | Thursday | Assigned to |  |  | Complete
|  | Level01 Linear Modeled | 40 | [5 empty] | Tim | Owen | Seth | 0 |  |  | Velocity | Stories | VelocityPercent
|  | Level01 Arena Modeled | 10 | 3 | 2 |  |  |  | Tim |  |  | 0 |  | Brandon | 4 | 4 | 100
|  | Level01 Textures | 15 | 3 | 3 | 4 | 2 | 3 | Jake |  |  | 0 |  | Tim | 0 | 2 | 0
|  | Mouse rotation | 4 | 4 | 3 | 3 | 0 |  | Brandon |  |  | 1 |  | Jake | 1 | 2 | 50
|  | Grounded movement | 5 | 5 | 5 | 5 | 2 | 0 | Brandon |  |  | 1 |  | Liam | 0 | 1 | 0
|  | Slope movement | 5 | 5 | 5 | 5 | 2 | 0 | Brandon |  |  | 1 |  | Owen | 3 | 3 | 100
|  | Import model asset | 3 | 3 | 0 | 0 | 0 | 0 | Jake |  |  | 1 |  | Seth | 0 | 2 | 0
|  | Create projectile | 3 | 1 | 1 | 1 | 0 | 0 | Owen |  |  | 1
|  | Move projectile | 2 | 1 | 1 | 1 | 0 | 0 | Owen |  |  | 1
|  | Import model asset | 1 | 1 | 1 | 1 | 0 | 0 | Seth |  |  | 0
|  | Have animation states for movement | 3 | 3 | 1 | 1 | 1 | 1 | Seth |  |  | 0
|  | Camera follows player | 5 | 3 | 0 |  |  |  | Brandon |  |  | 1
|  | Fireball Prefab | 5 | 5 | 4 | 2 | 2 | 2 | Liam |  |  | 0
|  | Expand Level and put invisible walls in | 2 | 1 | 0 | 0 | 0 | 0 | Owen |  |  | 1
|  | Remaining units (actual) | 103 | 38 | 26 | 23 | 9 | 6
|  | Remaining units (ideal) |  | 69.6 | 52.2 | 34.8 | 17.4 | 0
[12 empty] | 0 | 87
[12 empty] | 5 | 0
Note on D5: Olivier Gérardin: The sprint number.
Note on D6: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on A10: Olivier Gérardin: A unique Task ID
Note on B10: Olivier Gérardin: The Story this task will help complete.
Note on D10: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E10: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C31: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D31: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C32: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.

## Sprint 3
Sprint #3Tracking Sheet
|  | Project | Mitch the Lich
|  | Sprint # | 3
|  | Start date | 2018-09-10
Sprint Week
|  |  |  | 1 | 2 | 3 | 4 | 5
Task ID | Story ID | Description | Initial estimate | Friday | Monday | Tuesday | Wednesday | Thursday | Assigned to |  | Completed
|  | Level01 Storyboarded | 5 | 0 | 0 | 5 | 0 |  | Seth |  | 1 |  |  | Velocity | Stories | VelocityPercent
|  | Level01 Linear Modeled | 15 | 2 | 2 | 2 | 2 |  | Seth | Owen | 0 |  | Brandon | 3 | 3 | 100
|  | Level01 Arena Modeled | 15 | 2 | 2 | 5 | 1 |  | Seth | Owen | 0 |  | Tim | 0 | 3 | 0
|  | Level01 Textures | 15 | 5 | 5 | 2 | 1 | 1 | Jake |  | 0 |  | Jake | 0 | 3 | 0
|  | Health and damage system | 5 | 3 | 0 |  |  |  | Brandon |  | 1 |  | Liam | 0 | 2 | 0
|  | Buff management (regen) | 10 | 10 | 7 | 7 | 0 |  | Brandon |  | 1 |  | Owen | 2 | 4 | 50
|  | Fix shooting to mouse point | 5 | 1 | 0 |  |  |  | Owen |  | 1 |  | Seth | 2 | 4 | 50
|  | Shoot more than one projectile (extend) | 5 | 1 | 0 |  |  |  | Owen |  | 1
|  | Enemies moving towards player | 5 | 5 | 5 | 4 | 1 | 0 | Brandon |  | 1
|  | Have animation states for movement | 5 | 1 | 1 | 0 | 0 | 0 | Seth |  | 1
|  | UI Main menu | 3 | 2 | 2 | 1 |  |  | Tim |  | 0
|  | UI health+mana | 5 | [5 empty] | Tim |  | 0
|  | UI navigation menu | 3 | [5 empty] | TIm |  | 0
|  | Create fire/cast animation | 5 | [5 empty] | Jake |  | 0
|  | Import bunny model(s) | 5 | 2 | 3 | 0 |  |  | Jake |  | 0
|  | Finish Fireball prefab | 2 | 2 | 2 | 0 | 0 | 0 | Liam |  | 0
|  | Railgun and Shotgun prefab | 10 | [5 empty] | Liam |  | 0
|  | Remaining units (actual) | 118 | 36 | 29 | 26 | 5 | 1
|  | Remaining units (ideal) |  | 64 | 48 | 32 | 16 | 0
[12 empty] | 0 | 80
[12 empty] | 5 | 0
Note on D5: Olivier Gérardin: The sprint number.
Note on D6: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on A10: Olivier Gérardin: A unique Task ID
Note on B10: Olivier Gérardin: The Story this task will help complete.
Note on D10: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E10: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C32: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D32: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C33: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.

## Sprint 4
Sprint #4Tracking Sheet
|  | Project | Mitch the Lich
|  | Sprint # | 4
|  | Start date | 2018-09-17
Sprint Week
|  |  |  | 1 | 2 | 3 | 4 | 5
Task ID | Story ID | Description | Initial estimate | Monday | Tuesday | Wednesday | Thursday | Friday | Assigned to | Complete
|  | Level01 Linear Modeled Functionality | 20 | 18 | 18 | 15 | 15 | 8 | Seth | 0
|  | Level01 Textures | 15 | [5 empty] | Jake | 0 |  | Velocity | Stories | VelocityPercent
|  | Equip 2 spells | 5 | 0 |  |  |  |  | Owen | 1 | Brandon | 2 | 3 | 66.6667
|  | UI health+mana | 2 | 2 | 2 | 2 |  |  | Tim | 0 | Tim | 0 | 4 | 0
|  | UI navigation menu | 2 | 2 | 2 | 2 |  |  | Tim | 0 | Jake | 0 | 3 | 0
|  | Create fire/cast animation | 5 | [5 empty] | Jake | 0 | Liam | 0 | 1 | 0
|  | Dialogue box functionality | 5 | [5 empty] | Tim | 0 | Owen | 2 | 2 | 100
|  | Shoot at correct angle | 3 | 0 | 0 | 0 | 0 | 0 | Brandon | 1 | Seth | 0 | 2 | 0
|  | Terrain on layers | 5 | 5 | 5 | 5 | 5 | 5 | Seth | 0
|  | 3 different coloured particle effects | 10 | [5 empty] | Jake | 0
|  | Enemy shooting | 5 | 5 | 5 | 0 |  |  | Owen | 1
|  | Create hotbar UI + toggleable | 5 | 5 | 5 | 5 | 5 |  | Tim | 0
|  | Cutscene camera movement | 10 | [5 empty] | Tim | 0
|  | Bunny attack AI | 8 | 8 | 8 | 8 | 8 | 0 | Brandon | 1
|  | Railgun technology | 10 | 10 | 10 | 10 | 10 | 10 | Liam | 0
|  | implement movement buff | 5 | 15 | 15 | 15 | 15 | 12 | Brandon | 0
|  | Remaining units (actual) | 115 | 70 | 70 | 62 | 58 | 35
|  | Remaining units (ideal) |  | 45.6 | 34.2 | 22.8 | 11.4 | 0
[11 empty] | 0 | 57
[11 empty] | 5 | 0
Note on D5: Olivier Gérardin: The sprint number.
Note on D6: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on A10: Olivier Gérardin: A unique Task ID
Note on B10: Olivier Gérardin: The Story this task will help complete.
Note on D10: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E10: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C32: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D32: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C33: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.

## Sprint 5
Sprint #5Tracking Sheet
|  | Project | Mitch the Lich
|  | Sprint # | 5
|  | Start date | 24/09/2018
Sprint Week
|  |  |  | 1 | 2 | 3 | 4 | 5
Task ID | Story ID | Description | Initial estimate | Monday | Tuesday | Wednesday | Thursday | Friday | Assigned to | Complete |  |  |  | Velocity | Stories | VelocityPercent
|  | Level01 Linear Modeled Functionality | 8 |  |  |  |  | 8 | Seth | 0 |  |  | Brandon | 2 | 2 | 100
|  | Level01 Textures | 15 | [5 empty] | Jake | 0 |  |  | Tim | 2 | 4 | 50
|  | Enemy Spawning For Arena | 5 | 1 | 0 |  |  |  | Owen | 1 |  |  | Jake | 2 | 4 | 50
|  | UI health+mana | 2 | 1 |  |  |  |  | Tim | 0 |  |  | Liam | 0 | 1 | 0
|  | Create fire/cast animation | 5 | 0 |  |  |  |  | Jake | 1 |  |  | Owen | 2 | 2 | 100
|  | Dialogue box functionality | 5 | 1 | 1 | 1 | 0 |  | Tim | 1 |  |  | Seth | 0 | 2 | 0
|  | Shoot at correct angle | 3 | 0 |  |  |  |  | Brandon | 1
|  | Terrain on layers | 5 | 5 | 0 | 0 | 0 | 0 | Seth | 0 | EDIT:NOT COMPLETE
|  | 3 different coloured particle effects | 10 | 8 | 8 | 8 | 7 | 7 | Jake | 0
|  | Check Point Trigger Event | 2 | 0 |  |  |  |  | Owen | 1
|  | Create hotbar UI + toggleable | 5 | [5 empty] | Tim | 0
|  | Cutscene camera movement | 10 | 5 | 5 | 5 | 0 |  | Tim | 1
|  | Create Long Cast animation | 5 | 3 | 0 |  |  |  | Jake | 1
|  | Railgun technology | 10 | 10 | 10 | 10 | 8 | 6 | Liam | 0
|  | implement movement buff | 12 | 10 | 10 | 10 | 2 | 0 | Brandon | 1
|  | Remaining units (actual) | 102 | 44 | 34 | 34 | 17 | 21
|  | Remaining units (ideal) |  | 34.4 | 25.8 | 17.2 | 8.6 | 0
[12 empty] | 0 | 43
[12 empty] | 5 | 0
Note on D5: Olivier Gérardin: The sprint number.
Note on D6: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on A10: Olivier Gérardin: A unique Task ID
Note on B10: Olivier Gérardin: The Story this task will help complete.
Note on D10: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E10: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C32: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D32: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C33: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.

## Sprint 6
Sprint #6Tracking Sheet
|  | Project | Mitch the Lich
|  | Sprint # | 6
|  | Start date | 2018-10-04
Sprint Week
|  |  |  | 1 | 2 | 3 | 4 | 5
Task ID | Story ID | Description | Initial estimate | Monday | Tuesday | Wednesday | Thursday | Friday | Assigned to | Complete |  |  | Velocity | Stories | VelocityPercent
|  | Level01 Linear Modeled Functionality | 8 | 8 | 8 | 4 | 4 | 4 | Seth | 0 |  | Brandon | 1 | 1 | 100
|  | Level01 Story Implementation | 15 | 15 | 15 | 8 |  |  | Seth | 0 |  | Tim | 0 | 1 | 0
|  | Level01 Textures | 15 | 10 | 10 | 5 |  |  | Jake | 0 |  | Jake | 1 | 2 | 50
|  | Boss Shooting Ideas implemented | 5 | 5 | 5 | 0 |  |  | Owen | 1 |  | Liam | 0 | 1 | 0
|  | Animation's implemented | 5 | 5 | 5 | 2 | 2 | 2 | Seth | 0 |  | Owen | 3 | 3 | 100
|  | Fixed collision bug (bullet) | 5 | 5 | 5 | 0 |  |  | Owen | 1 |  | Seth | 0 | 3 | 0
|  | 3 different coloured particle effects | 7 | 7 | 5 | 0 |  |  | Jake | 1
|  | Added Delay to Player Shooting | 1 | 0 |  |  |  |  | Owen | 1
|  | Create hotbar UI + toggleable | 5 | [5 empty] | Tim | 0
|  | Railgun technology | 6 | 6 | 6 | 5 | 5 | 5 | Liam | 0
|  | Create particle effects for fireball and mitch idle | 5 | 5 | 5 | 0 |  |  | Brandon | 1
|  | Remaining units (actual) | 77 | 66 | 64 | 24 | 11 | 11
|  | Remaining units (ideal) |  | 42.4 | 31.8 | 21.2 | 10.6 | 0
[11 empty] | 0 | 53
[11 empty] | 5 | 0
Note on D5: Olivier Gérardin: The sprint number.
Note on D6: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on A10: Olivier Gérardin: A unique Task ID
Note on B10: Olivier Gérardin: The Story this task will help complete.
Note on D10: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E10: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C27: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D27: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C28: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.

## Sprint 7
Sprint #7Tracking Sheet
|  | Project | Mitch the Lich
|  | Sprint # | 7
|  | Start date | 2018-10-11
Sprint Week
|  |  |  | 1 | 2 | 3 | 4 | 5
Task ID | Story ID | Description | Initial estimate | Monday | Tuesday | Wednesday | Thursday | Friday | Assigned to | Complete |  |  | Velocity | Stories | VelocityPercent
|  | Level01 Linear Modeled Functionality | 8 | 8 | 8 | 8 | 8 |  | Seth | 0 |  | Brandon | 1 | 1 | 100
|  | Level01 Story Implementation | 15 | 15 | 15 | 8 |  |  | Seth | 0 |  | Tim | 0 | 1 | 0
|  | Level01 Textures | 15 | 10 | 10 | 5 | 0 |  | Jake | 1 |  | Jake | 1 | 2 | 50
|  | Implement Enemy Health | 5 | 5 | 5 | 0 |  |  | Owen | 1 |  | Liam | 0 | 1 | 0
|  | Animation's implemented | 5 | [5 empty] | Seth | 0 |  | Owen | 3 | 3 | 100
|  | Bunny Can Damage Player | 5 | 5 | 5 | 0 |  |  | Owen | 1 |  | Seth | 0 | 3 | 0
|  | 3 different coloured particle effects | 7 | 7 | 5 | 0 |  |  | Jake | 1
|  | Create Flamethrower spell | 1 | 0 |  |  |  |  | Owen | 1
|  | Create hotbar UI + toggleable | 5 | [5 empty] | Tim | 0
|  | Railgun technology | 5 | 5 | 5 | 4 | 4 | 4 | Liam | 0
|  | Abstract ProjectileLauncher and Create spell classes | 10 | 5 | 5 | 5 | 5 | 0 | Brandon | 1
|  | Remaining units (actual) | 81 | 60 | 58 | 30 | 17 | 4
|  | Remaining units (ideal) |  | 42.4 | 31.8 | 21.2 | 10.6 | 0
[11 empty] | 0 | 53
[11 empty] | 5 | 0
Note on D5: Olivier Gérardin: The sprint number.
Note on D6: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on A10: Olivier Gérardin: A unique Task ID
Note on B10: Olivier Gérardin: The Story this task will help complete.
Note on D10: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E10: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C26: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D26: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C27: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.

## Sprint 8
Sprint #8Tracking Sheet
|  | Project | Mitch the Lich
|  | Sprint # | 8
|  | Start date | 2018-10-18
Sprint Week
|  |  |  | 1 | 2 | 3 | 4 | 5
Task ID | Story ID | Description | Initial estimate | Monday | Tuesday | Wednesday | Thursday | Friday | Assigned to | Complete
|  | Implement mana delay, regen buff | 3 | 0 |  |  |  |  | Brandon
|  | Implement non-stacking buffs | 10 | [5 empty] | Brandon
|  | Implement slow,mana,heal, resist,burn | 10 | [5 empty] | Brandon
|  | Implement parabolic projectile | 7 | [5 empty] | Brandon
|  | Complete Opening Cinematic | 5 | 2 | 2 | 0 |  |  | Tim | 1
|  | Implement Actionbar | 5 | [5 empty] | Tim
|  | Create hotbar UI + toggleable | 5 | [5 empty] | Tim
|  | Player Controller | 7 | 2 | 0 |  |  |  | Owen | 1
|  | Shield Prefab | 1 | 1 | 0 |  |  |  | Owen | 1
|  | Story Implementation | 15 | 15 | 12 | 5 | 5 | 0 | Seth | 1
|  | Railgun Technology | 4 | 4 | 4 | 4 | 4 | 4 | Liam
|  | Scene Lighting | 8 | 5 | 4 | 4 | 4 | 4 | Jake
|  | Animation's implemented | 8 | 8 | 4 | 4 | 0 | 0 | Seth | 1
|  | Remaining units (actual) | 88 | 37 | 26 | 17 | 13 | 8
|  | Remaining units (ideal) |  | 42.4 | 31.8 | 21.2 | 10.6 | 0
[11 empty] | 0 | 53
[11 empty] | 5 | 0
Note on D5: Olivier Gérardin: The sprint number.
Note on D6: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on A10: Olivier Gérardin: A unique Task ID
Note on B10: Olivier Gérardin: The Story this task will help complete.
Note on D10: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E10: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C32: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D32: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C33: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.

## Sprint 9
Sprint #9Tracking Sheet
|  | Project | Mitch the Lich
|  | Sprint # | 9
|  | Start date | 2018-10-25
Sprint Week
|  |  |  | 1 | 2 | 3 | 4 | 5
Task ID | Story ID | Description | Initial estimate | Monday | Tuesday | Wednesday | Thursday | Friday | Assigned to | Complete
Brandon
|  | Implement non-stacking buffs | 10 | 10 | 0 |  |  |  | Brandon
|  | Implement slow,mana,heal, resist,burn | 10 | 8 | 6 |  |  |  | Brandon
|  | Implement parabolic projectile | 7 | 0 |  |  |  |  | Brandon
|  | Complete Opening Cinematic | 5 | 2 | 2 | 0 |  |  | Tim | 1
|  | Implement Actionbar | 5 | 2 | 0 |  |  |  | Tim | 1
|  | Arena Second Optional Level | 5 | [5 empty] | Tim
|  | Ice Spell that slows enemy | 5 | 0 |  |  |  |  | Owen | 1
|  | Rock Spell for Boss | 1 | 0 |  |  |  |  | Owen | 1
|  | Boss prefab | 1 | 0 |  |  |  |  | Owen | 1
|  | BigBunny prefab | 1 | 1 | 1 | 0 |  |  | Owen | 1
|  | Unique Spell For Enemies | 1 | 1 | 1 | 0 |  |  | Owen | 1
|  | Story Implementation | 12 | 12 | 8 | 0 | 0 | 0 | Seth
|  | Railgun Technology | 4 | 4 | 4 | 3 | 0 | 0 | Liam
|  | Vortex Texture | 5 | 0 |  |  |  |  | Jake | 1
|  | Sheild Texture | 5 | 0 |  |  |  |  | Jake | 1
|  | Scene Lighting | 4 | 4 | 0 |  |  |  | Jake | 1
|  | Remaining units (actual) | 81 | 44 | 22 | 3 | 0 | 0
|  | Remaining units (ideal) |  | 38.4 | 28.8 | 19.2 | 9.6 | 0
[11 empty] | 0 | 48
[11 empty] | 5 | 0
Note on D5: Olivier Gérardin: The sprint number.
Note on D6: Olivier Gérardin: The date of the first day of the sprint. Make it a Monday or date calculations will be inaccurate!
Note on A10: Olivier Gérardin: A unique Task ID
Note on B10: Olivier Gérardin: The Story this task will help complete.
Note on D10: Olivier Gérardin: This is the team's estimate of the quantity of work necessary to complete this task. The unit is an arbitrary "scrum work unit"; it's not important what you choose as long as you remain consistent across tasks. You can think of it as man.day or man.hour if you like. This is filled once before the sprint and does not change.
Note on E10: Olivier Gérardin: At the end of each day, fill in the estimated remaining scrum units for each task. Can be higher than the previous day if initial estimate was not accurate or other factors require more work.
Note on C32: Olivier Gérardin: The actual remaining scrum units at the end of the day. Shown in red if greater than the ideal (team is ahead of estimate) in green if lower (team is late).
Note on D32: Olivier Gérardin: This is the initial global estimate of this sprint's work effort in scrum units.
Note on C33: Olivier Gérardin: The ideal (theoretical) remaining scrum units at the end of the day, assuming initial work estimates are correct and work is equally spread across days.